## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
عبدالعزيز عصام آل الشيخ |  | 2. Save to one team member's Google drive
زيد محمد سعد الخثلان |  | 3. Share file with other team members
عبدالعزيز محمد الكثيري |  | 4. Edit First Names on this tab
عمر خالد العمودي |  | 5. Add your team name to the name of this document
اسامه صادق شبيطه |  | 6. For each sprint, duplicate the sprint template and change the start date
نواف عبدالحكيم العجلان
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Brief description |  |  |  | To Do |  | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2023-12-17 | 0 | 0 | 55 | 55
S1 | Product Architecture - Pre-planning | 19 | 15 |  | Done |  | Start Date: | 2023-12-17 | عبدالعزيز عصام آل الشيخ | 14 | 14 | 100% | 2023-12-18 | 0 | 0 | 55 | 49.7143
| Docmentation Format | 3 | 3 | عمر خالد العمودي | Done | 2023-12-25 | Sprint Length | 14 | زيد محمد سعد الخثلان | 5 | 5 | 100% | 2023-12-19 | 0 | 0 | 55 | 44.4286
| Documentation | 14 | 8 | عبدالعزيز عصام آل الشيخ | Done | 2023-12-22 | Hours Per Day: | 5.2857 | عبدالعزيز محمد الكثيري | 6 | 6 | 100% | 2023-12-20 | 0 | 0 | 55 | 39.1429
| Functional Requirments | 2 | 2 | عبدالعزيز محمد الكثيري | Done | 2023-12-23 |  |  | عمر خالد العمودي | 4 | 4 | 100% | 2023-12-21 | 0 | 0 | 55 | 33.8571
| Non-Functional Requirments | 2 | 2 | نواف عبدالحكيم العجلان | Done | 2023-12-23 |  |  | اسامه صادق شبيطه | 14 | 14 | 100% | 2023-12-22 | 19 | 19 | 36 | 28.5714
| Product Backlog | 5 | 4 | زيد محمد سعد الخثلان | Done | 2023-12-22 |  |  | نواف عبدالحكيم العجلان | 12 | 12 | 100% | 2023-12-23 | 4 | 23 | 32 | 23.2857
S2 | UI design |  |  |  | Done | [7 empty] | 2023-12-24 | 0 | 23 | 32 | 18
| color palette and theme | 7 | 5 | اسامه صادق شبيطه | Done | 2023-12-27 |  |  | Total: | 55 | 55 | 100% | 2023-12-25 | 3 | 26 | 29 | 12.7143
| icon design | 4 |  | عبدالعزيز محمد الكثيري | Done | 2023-12-27 | [6 empty] | 2023-12-26 | 0 | 26 | 29 | 7.4286
| Typography Selection | 1 | 1 | عمر خالد العمودي | Done | 2023-12-28 | [6 empty] | 2023-12-27 | 11 | 37 | 18 | 2.1429
| UI wireframe | 10 |  | نواف عبدالحكيم العجلان | Done | 2023-12-29 | [6 empty] | 2023-12-28 | 1 | 38 | 17 | 0
| Login Page Prototype | 7 | 5 | اسامه صادق شبيطه | Done | 2023-12-31 | [6 empty] | 2023-12-29 | 10 | 48 | 7 | 0
[5 empty] | To Do | [7 empty] | 2023-12-30 | 0 | 48 | 7 | 0
[5 empty] | To Do | [7 empty] | 2023-12-31 | 7 | 55 | 0 | 0
[5 empty] | To Do | [8 empty] | 19 | 74 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 93 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 112 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 131 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 150 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 150 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 165 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 184 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 200 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 219 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 227 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 245 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 254 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 273 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
[5 empty] | To Do | [8 empty] | 19 | 285 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
| S1 | Product Architecture Pre-planning | As a developer, I actively contribute to defining the system architecture, participate in selecting the technology stack, and implement key components. My role is to ensure a scalable, robust, and maintainable architecture that accommodates current and future functionalities. |  | 1-high | Done
| S2 | Simple UI/UX design | As a user, I want a user interface that's simple and straightforward |  | 1-high | Done
| S3 | Game design | As a user, I want a game design that offers an immersive and entertaining experience, capturing my interest and keeping me engaged throughout |  | 1-high | Done
| S4 | Database - User Score | As a user, I want a scoring system that keeps track of the scores I get after finishing a game. |  | 2-medium | To Do
| S5 | Database - User info | As a cross-platform user, I would like sync my progress on different platforms |  | 3-low | To Do
| S6 | Login page | As a user, I want a login page that provides a straightforward and secure authentication process, allowing me to access the application's features swiftly and reliably. I seek an intuitive interface that facilitates easy entry while ensuring the confidentiality and safety of my credentials. |  | 2-medium | Done
| S7 | UI - settings | As a user, I want to customize my personal settings as I like. |  | 3-low | In Progress
| S8 | Rewarding system | As a user, I want a rewarding system that acknowledges my achievements and progress within the game. I seek incentives such as badges, points, or unlockable content that provide recognition for my efforts and motivate continued engagement and exploration of the game's features |  | 2-medium | Done
| S9 | Leveling System | As a user, I want a leveling system that dynamically adapts to my progress, offering increasingly challenging yet achievable levels. I seek a system that tracks my accomplishments, providing a sense of achievement and motivating me to further engage with the game's content. |  | 2-medium | Done
| S10 | Game - more or less | As a parent/teacher, I seek a game that encourages children to grasp the concept of "more" and "less" in an engaging and educational manner. I hope for a game that cultivates their understanding of these concepts through interactive and enjoyable challenges, fostering their numerical comprehension in a fun learning environment. |  | 2-medium | In Progress
| S11 | Game - Flash cards | As a parent/teacher, I desire a flash cards game that enhances children's memory and recognition skills. The game should display pairs of objects on the cards, then hide them, challenging the child to remember and identify the locations of each matching pair. This game would be a valuable tool for developing cognitive skills in a playful and engaging manner. |  | 3-low | In Progress
| S12 | Game - Counting Objects | As a parent/teacher, I want a game that tests the child's ability to count objects and determine the number on the screen. |  | 3-low | Done
| S13 | Product Architecture Post-planning | As a developer, I want to review the established architecture, refine processes, and adapt to changes as needed. |  | 2-medium | Done
| S14 | Git & Github | As a development leader, I want the team to use Git & GitHub to coordinate our work with flexibility and more organization. |  | 3-low | Done
| S15 | MVC Pattern Architecture |  |  | 3-low | Done
| S16 | Project PowerPoint |  |  | 3-low | Done
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Brief description |  |  |  | To Do |  | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-01-13 | 0 | 0 | 63 | 63
S3 | Game design | 10 | 9 | عمر خالد العمودي | Done | 2024-01-19 | Start Date: | 2024-01-13 | عبدالعزيز عصام آل الشيخ | 10 | 10 | 100% | 2024-01-14 | 0 | 0 | 63 | 58.5
S6 | Login page |  |  |  | Done |  | Sprint Length | 14 | زيد محمد سعد الخثلان | 8 | 8 | 100% | 2024-01-15 | 0 | 0 | 63 | 54
| Login page UI/UX Implementaion | 8 | 8 | اسامه صادق شبيطه | Done | 2024-01-20 | Hours Per Day: | 4.5 | عبدالعزيز محمد الكثيري | 8 | 8 | 100% | 2024-01-16 | 0 | 0 | 63 | 49.5
S8 | Rewarding system |  |  |  | Done |  |  |  | عمر خالد العمودي | 10 | 10 | 100% | 2024-01-17 | 0 | 0 | 63 | 45
| Result Page UI/UX Implementation | 8 | 8 | زيد محمد سعد الخثلان | Done | 2024-01-22 |  |  | اسامه صادق شبيطه | 8 | 8 | 100% | 2024-01-18 | 0 | 0 | 63 | 40.5
| Confetti Implementation | 4 | 3 | نواف عبدالحكيم العجلان | Done | 2024-01-23 |  |  | نواف عبدالحكيم العجلان | 19 | 19 | 100% | 2024-01-19 | 10 | 10 | 53 | 36
S9 | Leveling System |  |  |  | Done | [7 empty] | 2024-01-20 | 23 | 33 | 30 | 31.5
| Leveling Logic Implementation | 10 | 9 | عبدالعزيز عصام آل الشيخ | Done | 2024-01-21 |  |  | Total: | 63 | 63 | 100% | 2024-01-21 | 10 | 43 | 20 | 27
S12 | Game - Counting Objects |  |  |  | Done | [7 empty] | 2024-01-22 | 8 | 51 | 12 | 22.5
| Game UI/UX Implementation | 8 | 8 | عبدالعزيز محمد الكثيري | Done | 2024-01-23 | [6 empty] | 2024-01-23 | 12 | 63 | 0 | 18
| Game Logic Implementation | 15 | 13 | نواف عبدالحكيم العجلان | Done | 2024-01-20 | [6 empty] | 2024-01-24 | 0 | 63 | 0 | 13.5
[5 empty] | To Do | [7 empty] | 2024-01-25 | 0 | 63 | 0 | 9
[5 empty] | To Do | [7 empty] | 2024-01-26 | 0 | 63 | 0 | 4.5
[5 empty] | To Do | [7 empty] | 2024-01-27 | 0 | 63 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 63 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 53 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 30 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 20 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S14 | Git & Github | 6 | 5 |  | Done | 2024-01-26 | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-01-23 | 0 | 0 | 15 | 15
| Created Branch Map | 4 | 3 | عبدالعزيز محمد الكثيري | Done | 2024-01-24 | Start Date: | 2024-01-23 | عبدالعزيز عصام آل الشيخ | 0 | 0 | 0% | 2024-01-24 | 4 | 4 | 11 | 13.0714
| Added README.md file | 2 | 2 | نواف عبدالحكيم العجلان | Done | 2024-01-26 | Sprint Length | 14 | زيد محمد سعد الخثلان | 2 | 2 | 100% | 2024-01-25 | 0 | 4 | 11 | 11.1429
S15 | MVC Pattern Architecture | 6 | 6 |  | Done | 2024-01-29 | Hours Per Day: | 1.9286 | عبدالعزيز محمد الكثيري | 7 | 7 | 100% | 2024-01-26 | 8 | 12 | 3 | 9.2143
| Modle Modified | 2 | 2 | اسامه صادق شبيطه | Done | 2024-01-28 |  |  | عمر خالد العمودي | 2 | 2 | 100% | 2024-01-27 | 0 | 12 | 3 | 7.2857
| Player perspective in View | 2 | 2 | زيد محمد سعد الخثلان | Done | 2024-01-28 |  |  | اسامه صادق شبيطه | 2 | 2 | 100% | 2024-01-28 | 4 | 16 | -1 | 5.3571
| Contorller intercation with Modle | 2 | 2 | عمر خالد العمودي | Done | 2024-01-29 |  |  | نواف عبدالحكيم العجلان | 2 | 2 | 100% | 2024-01-29 | 8 | 24 | -9 | 3.4286
S16 | Project PowerPoint | 3 | 2 | عبدالعزيز محمد الكثيري | Done | 2024-01-30 | [6 empty] | 2024-01-30 | 3 | 27 | -12 | 1.5
[5 empty] | To Do |  |  |  | Total: | 15 | 15 | 100% | 2024-01-31 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-01 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-02 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-03 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-04 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-05 | 0 | 27 | -12 | 0
[5 empty] | To Do | [7 empty] | 2024-02-06 | 0 | 27 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 27 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 23 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 23 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 15 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 15 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 3 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")